## Sprint Summary
Sprint-Level Effort Summary
Sprint | Tasks | Work Hours (h) | Share | Buffered Hours | Labour Cost (€) | Cost incl. Buffer (€)
Sprint 1 | 42 | 25 | 5.977% | 30 | 750 | 900
Sprint 2 | 37 | 89.25 | 21.34% | 107.1 | 2677.5 | 3213
Sprint 3 | 46 | 137.0333 | 32.76% | 164.44 | 4111 | 4933.2
Sprint 4 | 54 | 143 | 34.19% | 171.6 | 4290 | 5148
Sprint 5 | 11 | 24 | 5.738% | 28.8 | 720 | 864
TOTAL | 190 | 418.2833 | 100% | 501.94 | 12548.5 | 15058.2
Assumption |  | Value
Hourly labour rate (€) |  | 30
Contingency / buffer |  | 20%

## Issue Detail
Plug & Wifi — Jira Task-Level Working Hours
Issue Key | Summary | Status | Assignee | Parent Key | Parent / Epic | Sprint Coverage | Original Estimate (h) | Time Spent (h) | Created | Resolved
G4PW-7 | Core Product Backlog Structural Creation | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 | 16 | 16 | 25/May/26 1:59 AM | 04/Jun/26 3:58 PM
G4PW-8 | UI/UX Mockups & Wireframe Generation | Done | Youssef Bouarada | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 25/May/26 2:01 AM | 04/Jun/26 3:56 PM
G4PW-10 | Environment Setup & Emulator Configuration | Done | Wenfei Song | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 25/May/26 2:02 AM | 04/Jun/26 3:57 PM
G4PW-11 | Explore Datasets and Identify Quality Issues | Done | Adam Treanor | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 25/May/26 2:03 AM | 04/Jun/26 3:56 PM
G4PW-12 | Investigate Backend Frameworks & Map APIs | Done | sunmin.lee | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 | 16 | 5 | 25/May/26 2:04 AM | 31/May/26 10:13 PM
G4PW-55 | Local Frontend Environment Configuration | Done | Peiyou Yao | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 5:36 PM | 04/Jun/26 5:37 PM
G4PW-56 | Frontend Project Initialization (Vite + TS) | Done | Peiyou Yao | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 5:37 PM | 04/Jun/26 5:46 PM
G4PW-57 | Document Unified Formatting Automation Script | Done | Peiyou Yao | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:39 PM | 04/Jun/26 5:46 PM
G4PW-58 | UI-Based Frontend Page Structural Development | Done | Peiyou Yao | G4PW-48 | Landing Page & Navigation | Sprint 1 |  |  | 04/Jun/26 5:41 PM | 04/Jun/26 5:46 PM
G4PW-59 | Conditional Mocking & Unified API Fetcher Architecture | Done | Peiyou Yao | G4PW-52 | Quality Assurance & Automated Testing | Sprint 1 |  |  | 04/Jun/26 5:41 PM | 04/Jun/26 5:46 PM
G4PW-60 | Frontend UI Layout Scaffold & Skeleton Code | Done | Youssef Bouarada | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 5:48 PM | 04/Jun/26 6:11 PM
G4PW-61 | User Requirement Interviews & Spec Engineering | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:49 PM | 04/Jun/26 6:11 PM
G4PW-62 | Writing, Transcribing & Reviewing Project Docs | Done | Youssef Bouarada | G4PW-54 | Academic Deliverables & Presentations | Sprint 1 |  |  | 04/Jun/26 5:50 PM | 04/Jun/26 6:11 PM
G4PW-63 | User Stories Composition & Estimation | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:50 PM | 04/Jun/26 6:11 PM
G4PW-64 | Backlog Grooming & Requirement Refining | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:50 PM | 04/Jun/26 6:11 PM
G4PW-65 | Active Cross-Functional Meeting Participation | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:51 PM | 04/Jun/26 6:11 PM
G4PW-66 | Team Role Allocation & Acceptance Criteria Definition | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:51 PM | 04/Jun/26 6:11 PM
G4PW-67 | Target User Personas Architecture Definition | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 5:51 PM | 04/Jun/26 6:11 PM
G4PW-68 | Academic Documentation(Team contract, meeting minutes, and sync agendas) | Done | Tzu Yu Chang | G4PW-54 | Academic Deliverables & Presentations | Sprint 1 |  |  | 04/Jun/26 5:54 PM | 04/Jun/26 6:35 PM
G4PW-69 | Cloud Hosting Architecture Draft | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 5:58 PM | 04/Jun/26 6:35 PM
G4PW-70 | Conduct automated testing tools investigation | Done | Tzu Yu Chang | G4PW-52 | Quality Assurance & Automated Testing | Sprint 1 |  |  | 04/Jun/26 5:59 PM | 04/Jun/26 6:35 PM
G4PW-71 | Configure automated trigger events, status checks, and branch restriction rules for automated PR builds | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:00 PM | 04/Jun/26 6:35 PM
G4PW-72 | Investigate and initialize base GitHub Actions CI/CD workflow YAML pipeline files | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:01 PM | 04/Jun/26 6:35 PM
G4PW-73 | Author, review, and publish the CONTRIBUTING.md file establishing strict team guidelines for Git workflows | Done | Tzu Yu Chang | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 6:01 PM | 04/Jun/26 6:35 PM
G4PW-74 | Configure the team branching strategy (GitFlow) and setup main/develop branch protections | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:03 PM | 04/Jun/26 6:35 PM
G4PW-75 | Initialize the GitHub monorepo repository architecture | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:03 PM | 04/Jun/26 6:35 PM
G4PW-76 | Establish the Jira team board, configure custom workflows | Done | Tzu Yu Chang | G4PW-53 | Agile Project Management | Sprint 1 |  |  | 04/Jun/26 6:03 PM | 04/Jun/26 6:35 PM
G4PW-77 | Fetch_Venues API & Data Ingestion Setup | Done | Adam Treanor | G4PW-2 | Venue Discovery & Search | Sprint 1 |  |  | 04/Jun/26 6:18 PM | 04/Jun/26 6:30 PM
G4PW-78 | Transport_Model Feature Engineering | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 1 |  |  | 04/Jun/26 6:18 PM | 04/Jun/26 6:30 PM
G4PW-79 | Noise_Model Acoustic Conditioning Baseline Algorithm | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 1 |  |  | 04/Jun/26 6:19 PM | 04/Jun/26 6:30 PM
G4PW-80 | Wifi_Model Capacity & Score Weighting Setup | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 1 |  |  | 04/Jun/26 6:19 PM | 04/Jun/26 6:30 PM
G4PW-81 | Plug_Model Localized Concentration Weighting Setup | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 1 |  |  | 04/Jun/26 6:27 PM | 04/Jun/26 6:30 PM
G4PW-82 | Ratings_Model Feature Engineering & Aggregate Matrix | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 1 |  |  | 04/Jun/26 6:27 PM | 04/Jun/26 6:30 PM
G4PW-83 | Flask Architecture Prototype Initialization | Done | sunmin.lee | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:36 PM | 04/Jun/26 6:42 PM
G4PW-84 | FastAPI Core Architecture Prototype Setup | Done | sunmin.lee | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:37 PM | 04/Jun/26 6:42 PM
G4PW-85 | PostgreSQL Local Instance Configuration & Setup | Done | sunmin.lee | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:37 PM | 04/Jun/26 6:42 PM
G4PW-86 | Relational Database Schema Design & Normalization | Done | sunmin.lee | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 6:37 PM | 04/Jun/26 6:42 PM
G4PW-87 | Map API Routing Capabilities Investigation | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 1 |  |  | 04/Jun/26 6:38 PM | 04/Jun/26 6:42 PM
G4PW-88 | Mock API Contract Specification Documentation | Done | sunmin.lee | G4PW-52 | Quality Assurance & Automated Testing | Sprint 1 |  |  | 04/Jun/26 6:38 PM | 04/Jun/26 6:42 PM
G4PW-89 | React Native Learning & Practice | Done | Wenfei Song | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 1 |  |  | 04/Jun/26 7:59 PM | 04/Jun/26 8:00 PM
G4PW-90 | UI Framework Implementation & Testing | Done | Wenfei Song | G4PW-47 | Mobile & Responsive UX | Sprint 1 |  |  | 04/Jun/26 7:59 PM | 04/Jun/26 8:00 PM
G4PW-91 | Sprint 1 Syncs, Cross-Functional Alignments & Faculty Reviews | Done | Tzu Yu Chang | G4PW-53 | Agile Project Management | Sprint 1 | 4 |  | 04/Jun/26 8:05 PM | 05/Jun/26 5:45 PM
G4PW-25 | UI Form Implementation & Client-Side Validation | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 2 | 4 |  | 03/Jun/26 5:22 PM | 20/Jun/26 8:21 PM
G4PW-27 | Security & Password Hashing | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 2 | 2 | 3 | 03/Jun/26 5:22 PM | 08/Jun/26 4:25 PM
G4PW-92 | Sprint 2 Syncs, Cross-Functional Alignments & Faculty Reviews | Done | Tzu Yu Chang | G4PW-53 | Agile Project Management | Sprint 2 | 4 | 0.75 | 04/Jun/26 8:46 PM | 19/Jun/26 3:57 PM
G4PW-94 | App UI Form Implementation & Client-Side Validation | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 2 | 3 |  | 04/Jun/26 10:09 PM | 17/Jun/26 11:40 AM
G4PW-96 | POST /api/auth/register API Endpoint | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 2 | 1 | 1 | 04/Jun/26 10:16 PM | 08/Jun/26 4:26 PM
G4PW-97 | API Integration & Mobile Routing Navigation | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 2 | 2 |  | 04/Jun/26 10:21 PM | 17/Jun/26 8:50 PM
G4PW-105 | POST /api/auth/login API & JWT Generation | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 2 | 1 | 2 | 04/Jun/26 10:54 PM | 08/Jun/26 7:43 PM
G4PW-106 | Login UI Form & Error Handling | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 2 | 1 |  | 04/Jun/26 10:55 PM | 18/Jun/26 3:35 PM
G4PW-107 | Login App UI & Error Handling | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 2 | 1 |  | 04/Jun/26 10:56 PM | 17/Jun/26 11:41 AM
G4PW-110 | Native Storage & Session Hydration | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 2 | 2 |  | 04/Jun/26 11:23 PM | 17/Jun/26 8:50 PM
G4PW-111 | GET /api/users/me Endpoint & Token Validation Logic | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 2 | 1 | 3 | 04/Jun/26 11:27 PM | 11/Jun/26 12:51 PM
G4PW-117 | Native Logout & State Clearance | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 2 | 1 |  | 05/Jun/26 12:32 AM | 18/Jun/26 4:05 PM
G4PW-118 | POST /api/auth/logout API Endpoint | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 2 | 1 | 1 | 05/Jun/26 12:33 AM | 17/Jun/26 9:59 AM
G4PW-125 | Map View Location Search & Proximity UI | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 2 | 3 |  | 05/Jun/26 12:47 AM | 18/Jun/26 4:05 PM
G4PW-126 | GET /api/venues Geospatial Logic & Proximity Sorting | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 2 | 3 | 3 | 05/Jun/26 12:49 AM | 16/Jun/26 3:27 PM
G4PW-129 | Native Date/Time Picker & Availability Integration | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 2 | 2 |  | 05/Jun/26 12:57 AM | 18/Jun/26 4:05 PM
G4PW-130 | Availability Filtering Logic & Database Joins | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 2 | 3 | 3 | 05/Jun/26 12:57 AM | 11/Jun/26 11:00 AM
G4PW-134 | GET /api/venues Dynamic Query Builder & Duration Logic | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 2 | 5 | 5 | 05/Jun/26 1:25 AM | 16/Jun/26 7:31 PM
G4PW-137 | Native Map Layout & Carousel Initialization | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 2 | 2 |  | 05/Jun/26 1:30 AM | 17/Jun/26 11:41 AM
G4PW-139 | Venue Card UI Component (Grid Item) | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 2 | 3 |  | 05/Jun/26 1:35 AM | 18/Jun/26 3:33 PM
G4PW-141 | API Payload Verification (Venue Summary DTO) | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 2 | 1 | 1 | 05/Jun/26 1:41 AM | 16/Jun/26 9:53 AM
G4PW-144 | Pagination Support for GET /api/venues | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 2 | 2 | 2 | 05/Jun/26 3:04 PM | 16/Jun/26 3:26 PM
G4PW-149 | Foundational Venue Detail Page & Sections Implementation | Done | Peiyou Yao | G4PW-3 | Venue Detail | Sprint 2 | 3 |  | 05/Jun/26 4:07 PM | 18/Jun/26 3:33 PM
G4PW-151 | GET /api/venues/{venue_id} Profile Endpoint Development | Done | sunmin.lee | G4PW-3 | Venue Detail | Sprint 2 | 2 | 2 | 05/Jun/26 4:09 PM | 10/Jun/26 3:56 PM
G4PW-153 | Booking Panel Widget & Price Calculator UI | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 2 | 2 |  | 05/Jun/26 4:13 PM | 18/Jun/26 3:33 PM
G4PW-155 | POST /api/bookings Endpoint & State Modification Logic | Done | sunmin.lee | G4PW-4 | Booking & Payments | Sprint 2 | 2 | 2 | 05/Jun/26 4:15 PM | 11/Jun/26 11:24 AM
G4PW-158 | Native Confirmation Screen Navigation | Done | Wenfei Song | G4PW-4 | Booking & Payments | Sprint 2 | 1 |  | 05/Jun/26 4:17 PM | 18/Jun/26 4:05 PM
G4PW-168 | Search Hub UI & Conditional Empty State Implementation | Done | Peiyou Yao | G4PW-48 | Landing Page & Navigation | Sprint 2 | 4 |  | 05/Jun/26 5:29 PM | 18/Jun/26 3:33 PM
G4PW-169 | Native App Initial Landing Screen & No-Results Overlay | Done | Wenfei Song | G4PW-48 | Landing Page & Navigation | Sprint 2 | 2 |  | 05/Jun/26 5:30 PM | 15/Jun/26 9:54 PM
G4PW-171 | Develop PostgreSQL Database Seed Script | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 2 | 2 | 3 | 05/Jun/26 5:49 PM | 09/Jun/26 2:10 PM
G4PW-172 | Automate Seed Execution on Staging Deployments | Done | Tzu Yu Chang | G4PW-5 | Provider / Venue Management | Sprint 2 | 2 |  | 05/Jun/26 5:52 PM | 11/Jun/26 2:03 PM
G4PW-174 | FastAPI Backend Staging Deployment & Managed Database | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2 | 5 | 10 | 05/Jun/26 5:55 PM | 09/Jun/26 3:30 PM
G4PW-175 | API Gateway CORS Configuration & Frontend Environment Setup | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2 | 2 | 2 | 05/Jun/26 5:56 PM | 10/Jun/26 6:53 PM
G4PW-176 | Expand GitHub Actions CI Pipeline | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2 | 2 | 1 | 05/Jun/26 5:59 PM | 15/Jun/26 10:13 PM
G4PW-178 | Implement Pytest Suite for Core S2 APIs | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2 | 5 | 3.5 | 05/Jun/26 6:10 PM | 15/Jun/26 9:56 PM
G4PW-180 | Cloud Staging CORS & JWT Cross-Origin Verification | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2 | 2 | 1 | 05/Jun/26 6:12 PM | 15/Jun/26 10:35 PM
G4PW-184 | React Frontend Staging Deployment & Multi-Stage Dockerization | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2 | 3 | 2 | 10/Jun/26 7:25 PM | 11/Jun/26 2:15 PM
G4PW-26 | User Table Schema Design & Constraints Setup | Done | Adam Treanor | G4PW-1 | User Authentication & Account | Sprint 2, Sprint 3 | 2 |  | 03/Jun/26 5:22 PM | 22/Jun/26 1:28 PM
G4PW-95 | API Integration & Auto-Login Routing | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 2, Sprint 3 | 2 |  | 04/Jun/26 10:11 PM | 25/Jun/26 7:45 PM
G4PW-98 | Provider Portal Navigation & UI Form | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 3 | 2 |  | 04/Jun/26 10:37 PM | 01/Jul/26 12:34 AM
G4PW-100 | Registration API Expansion for Provider Role | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 3 | 1 | 1 | 04/Jun/26 10:42 PM | 23/Jun/26 7:38 PM
G4PW-101 | API Integration & Onboarding Workspace Routing | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 3 | 1 |  | 04/Jun/26 10:44 PM | 25/Jun/26 7:46 PM
G4PW-102 | Mobile Menu Entry & Provider UI Form | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 3 | 2 |  | 04/Jun/26 10:45 PM | 25/Jun/26 10:03 PM
G4PW-103 | API Integration & Mobile Onboarding Routing | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 3 | 1 |  | 04/Jun/26 10:46 PM | 30/Jun/26 10:40 AM
G4PW-116 | Logout Logic & State Clearance | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 2, Sprint 3 | 1 |  | 05/Jun/26 12:31 AM | 25/Jun/26 7:49 PM
G4PW-121 | Navigation Guards & Conditional UI | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 3 | 2 |  | 05/Jun/26 12:39 AM | 25/Jun/26 10:03 PM
G4PW-122 | RBAC Middleware & Endpoint Interception | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 3 | 3 | 3 | 05/Jun/26 12:39 AM | 25/Jun/26 8:56 AM
G4PW-124 | Grid View Location Search & Distance UI | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3 | 3 |  | 05/Jun/26 12:47 AM | 07/Jul/26 12:35 PM
G4PW-128 | Date/Time Picker UI & Availability Integration | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3 | 2 |  | 05/Jun/26 12:56 AM | 07/Jul/26 12:36 PM
G4PW-132 | Comprehensive Filter UI & Client-Side Reactivity | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3 | 5 |  | 05/Jun/26 1:23 AM | 01/Jul/26 12:27 AM
G4PW-133 | Native Filter Drawer & Dynamic Rendering | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3 | 5 |  | 05/Jun/26 1:24 AM | 22/Jun/26 7:42 PM
G4PW-140 | Native Venue Card Component (Carousel Item) | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3 | 3 |  | 05/Jun/26 1:36 AM | 22/Jun/26 7:42 PM
G4PW-143 | Grid Initializer & "More Venues" Pagination Logic | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3 | 2 |  | 05/Jun/26 3:03 PM | 20/Jun/26 8:22 PM
G4PW-146 | Layout Toggle Controls & Global State Preservation | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 3 | 2 |  | 05/Jun/26 3:41 PM | 18/Jun/26 3:33 PM
G4PW-147 | Native View Toggle & Shared Controller | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 3 | 2 |  | 05/Jun/26 3:42 PM | 22/Jun/26 7:42 PM
G4PW-160 | Develop Deterministic Rule-Based Suitability Scoring Engine & Seed Weights | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 2, Sprint 3 | 8 | 8 | 05/Jun/26 5:11 PM | 22/Jun/26 1:29 PM
G4PW-163 | Render Suitability Score Badge on Map Carousel | Done | Wenfei Song | G4PW-6 | ML Recommendation & AI Features | Sprint 2, Sprint 3 | 1 |  | 05/Jun/26 5:17 PM | 22/Jun/26 7:42 PM
G4PW-179 | FastAPI Health Check Endpoint & Post-Deployment CD Ping | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 2, Sprint 3 | 1 |  | 05/Jun/26 6:11 PM | 23/Jun/26 4:00 PM
G4PW-182 | Sprint 2 Time Budget Monitoring & S3 Backlog Grooming | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 2, Sprint 3 | 8 |  | 05/Jun/26 6:28 PM | 07/Jul/26 12:40 PM
G4PW-192 | Develop User Bookings API Endpoint | Done | sunmin.lee | G4PW-4 | Booking & Payments | Sprint 3 | 3 | 3 | 20/Jun/26 9:08 PM | 23/Jun/26 8:18 PM
G4PW-193 | Build "My Bookings" Dashboard & Tabs UI | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 3 | 3 |  | 20/Jun/26 9:13 PM | 01/Jul/26 12:24 AM
G4PW-194 | Implement Cancellation Logic & Inventory Deallocation | Done | sunmin.lee | G4PW-4 | Booking & Payments | Sprint 3 | 2 | 2 | 20/Jun/26 9:15 PM | 24/Jun/26 9:14 AM
G4PW-195 | Develop Cancellation Intercept Modal & API Binding | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 3 | 2 |  | 20/Jun/26 9:17 PM | 01/Jul/26 12:28 AM
G4PW-200 | Implement Final Step Verification & T&Cs Lock(App) | Done | Wenfei Song | G4PW-5 | Provider / Venue Management | Sprint 3 | 2 |  | 20/Jun/26 10:44 PM | 30/Jun/26 10:40 AM
G4PW-202 | Build Capacity-Checking Inventory Booking Logic | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 3 | 3 | 3 | 20/Jun/26 11:02 PM | 24/Jun/26 5:53 PM
G4PW-203 | Implement Slot Modification Guard Rails | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 3 | 3 | 3 | 20/Jun/26 11:03 PM | 27/Jun/26 9:21 AM
G4PW-206 | Build Live Aggregation KPI Metrics Endpoint | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 3 | 4 | 4 | 20/Jun/26 11:12 PM | 25/Jun/26 12:12 PM
G4PW-207 | Implement Real-Time Feed for Upcoming Arrivals | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 3 | 3 | 3 | 20/Jun/26 11:13 PM | 27/Jun/26 8:51 AM
G4PW-208 | Build Host KPI & Dynamic Booking List Grid | Done | Peiyou Yao | G4PW-5 | Provider / Venue Management | Sprint 3 | 4 |  | 20/Jun/26 11:14 PM | 01/Jul/26 12:34 AM
G4PW-210 | Build Verified Survey Metrics & Aggregation Engine | Done | sunmin.lee | G4PW-49 | Reviews & Ratings | Sprint 3 | 4 | 4 | 20/Jun/26 11:20 PM | 27/Jun/26 10:47 AM
G4PW-211 | Post-Review Callback Pipeline & Real-Time Star Rating Synchronization | Done | sunmin.lee | G4PW-49 | Reviews & Ratings | Sprint 3 | 3 | 3 | 20/Jun/26 11:23 PM | 28/Jun/26 10:38 AM
G4PW-215 | Build Venue Listing Creation API & Database Schema Integration | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 3 | 3 | 3 | 20/Jun/26 11:40 PM | 29/Jun/26 6:56 PM
G4PW-217 | Build Admin Overview Aggregations & RBAC Protections | Done | sunmin.lee | G4PW-50 | Admin / System Operations | Sprint 3 | 4 | 4 | 20/Jun/26 11:48 PM | 28/Jun/26 8:51 AM
G4PW-218 | Implement Venue Suspension & Emergency Cancellation API | Done | sunmin.lee | G4PW-50 | Admin / System Operations | Sprint 3 | 3 | 3 | 20/Jun/26 11:49 PM | 28/Jun/26 11:53 AM
G4PW-221 | Integrate OpenStreetMap & Render Venue Pins | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 3 | 4 |  | 20/Jun/26 11:54 PM | 25/Jun/26 7:32 PM
G4PW-225 | Build POST /api/auth/refresh Endpoint & Security Schema | Done | sunmin.lee | G4PW-1 | User Authentication & Account | Sprint 3 | 4 | 4 | 22/Jun/26 6:49 PM | 24/Jun/26 1:37 PM
G4PW-227 | Build Native Secure Storage Token Rotation Controller | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 3 | 3 |  | 22/Jun/26 6:51 PM | 23/Jun/26 2:44 PM
G4PW-229 | Develop DELETE /api/favorites/{venue_id} Endpoint | Done | sunmin.lee | G4PW-4 | Booking & Payments | Sprint 3 | 3 | 3 | 22/Jun/26 6:53 PM | 25/Jun/26 10:56 AM
G4PW-231 | Implement Deletion Action Bindings on Mobile Map Carousel | Done | Wenfei Song | G4PW-4 | Booking & Payments | Sprint 3 | 2 |  | 22/Jun/26 6:54 PM | 23/Jun/26 2:44 PM
G4PW-233 | Database Configuration Refactoring & Driver Tuning | Done | sunmin.lee | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 3 | 2 | 0.033333 | 22/Jun/26 6:57 PM | 23/Jun/26 7:38 PM
G4PW-240 | Build MTA Ridership Data Pipeline | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 3 | 6 |  | 01/Jul/26 12:14 AM | 01/Jul/26 12:15 AM
G4PW-241 | Derive Busyness Training Features from MTA Data | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 3 | 6 |  | 01/Jul/26 12:18 AM | 01/Jul/26 12:19 AM
G4PW-242 | Implement KNN Area Busyness Prediction Model | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 3 | 4 |  | 01/Jul/26 12:19 AM | 01/Jul/26 12:19 AM
G4PW-109 | App Initialization & Session Hydration | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 2, Sprint 3, Sprint 4 | 2 |  | 04/Jun/26 11:22 PM | 24/Jul/26 10:01 AM
G4PW-113 | In-Context Auth Modal & Checkout Progression | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 3, Sprint 4 | 3 |  | 04/Jun/26 11:34 PM | 24/Jul/26 10:01 AM
G4PW-114 | In-Context Auth Overlay & Checkout Progression | Done | Wenfei Song | G4PW-1 | User Authentication & Account | Sprint 3, Sprint 4 | 3 |  | 04/Jun/26 11:35 PM | 30/Jul/26 2:28 PM
G4PW-120 | Route Guards & UI Conditional Rendering | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 3, Sprint 4 | 2 |  | 05/Jun/26 12:38 AM | 24/Jul/26 9:47 AM
G4PW-136 | User-Agent Detection & Default Layout Routing | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 2, Sprint 3, Sprint 4 | 2 |  | 05/Jun/26 1:29 AM | 24/Jul/26 10:01 AM
G4PW-150 | Native Venue Profile Screen & Bottom Call-to-Action Layout | Done | Wenfei Song | G4PW-3 | Venue Detail | Sprint 2, Sprint 3, Sprint 4 | 3 |  | 05/Jun/26 4:08 PM | 30/Jul/26 2:27 PM
G4PW-154 | Native Booking Bottom Sheet & State Binding | Done | Wenfei Song | G4PW-4 | Booking & Payments | Sprint 2, Sprint 3, Sprint 4 | 2 |  | 05/Jun/26 4:14 PM | 13/Jul/26 9:39 PM
G4PW-157 | Order Confirmation Routing & Receipt View | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 2, Sprint 3, Sprint 4 | 1 |  | 05/Jun/26 4:17 PM | 24/Jul/26 9:46 AM
G4PW-161 | Pass-through Rendering for Suitability Score | Done | Peiyou Yao | G4PW-6 | ML Recommendation & AI Features | Sprint 2, Sprint 3, Sprint 4 | 1 |  | 05/Jun/26 5:12 PM | 24/Jul/26 10:01 AM
G4PW-162 | Pass-through Rendering for Suitability Score | Done | Peiyou Yao | G4PW-6 | ML Recommendation & AI Features | Sprint 2, Sprint 3, Sprint 4 | 1 |  | 05/Jun/26 5:15 PM | 24/Jul/26 10:01 AM
G4PW-165 | Global RWD Breakpoints & CSS Media Queries Optimization | Done | Peiyou Yao | G4PW-47 | Mobile & Responsive UX | Sprint 2, Sprint 3, Sprint 4 | 4 |  | 05/Jun/26 5:22 PM | 24/Jul/26 10:00 AM
G4PW-166 | Refactor Global Interactivity Tap Target Dimensions | Done | Peiyou Yao | G4PW-47 | Mobile & Responsive UX | Sprint 2, Sprint 3, Sprint 4 | 2 |  | 05/Jun/26 5:27 PM | 24/Jul/26 10:00 AM
G4PW-183 | User Acceptance Testing | Done | Youssef Bouarada | G4PW-53 | Agile Project Management | Sprint 2, Sprint 3, Sprint 4 | 3 |  | 05/Jun/26 6:29 PM | 30/Jul/26 2:21 PM
G4PW-196 | Develop Cancellation Intercept Drawer & API Binding | Done | Wenfei Song | G4PW-4 | Booking & Payments | Sprint 3, Sprint 4 | 2 |  | 20/Jun/26 9:51 PM | 30/Jul/26 2:27 PM
G4PW-197 | Design & Implement Multi-Step Form UI Wizard | Done | Peiyou Yao | G4PW-5 | Provider / Venue Management | Sprint 3, Sprint 4 | 3 |  | 20/Jun/26 9:54 PM | 24/Jul/26 10:01 AM
G4PW-199 | Implement Final Step Verification & T&Cs Lock(Web) | Done | Peiyou Yao | G4PW-5 | Provider / Venue Management | Sprint 3, Sprint 4 | 2 |  | 20/Jun/26 10:43 PM | 24/Jul/26 10:00 AM
G4PW-201 | Enforce Search Filter Security & Vetting Logic Testing | Done | sunmin.lee | G4PW-5 | Provider / Venue Management | Sprint 4 | 3 | 3 | 20/Jun/26 10:54 PM | 20/Jul/26 6:39 PM
G4PW-204 | Build Host Capacity/Policy Config UI & Validation | Done | Peiyou Yao | G4PW-5 | Provider / Venue Management | Sprint 3, Sprint 4 | 3 |  | 20/Jun/26 11:09 PM | 24/Jul/26 10:00 AM
G4PW-212 | Implement Deterministic Rule-Based Suitability Weight Equations | Done | Adam Treanor | G4PW-49 | Reviews & Ratings | Sprint 3, Sprint 4 | 3 |  | 20/Jun/26 11:26 PM | 30/Jul/26 2:22 PM
G4PW-213 | Render Verified Metrics & Match Badges on Web | Done | Tzu Yu Chang | G4PW-49 | Reviews & Ratings | Sprint 3, Sprint 4 | 3 |  | 20/Jun/26 11:27 PM | 30/Jul/26 2:23 PM
G4PW-214 | Render Verified Metrics & Match Badges on Mobile | Done | Wenfei Song | G4PW-49 | Reviews & Ratings | Sprint 3, Sprint 4 | 3 |  | 20/Jun/26 11:29 PM | 24/Jul/26 9:55 AM
G4PW-219 | Build Minimalist Web Admin Dashboard Grid | Done | Peiyou Yao | G4PW-50 | Admin / System Operations | Sprint 3, Sprint 4 | 2 |  | 20/Jun/26 11:50 PM | 24/Jul/26 9:45 AM
G4PW-220 | Implement Administrative Intercept Modals | Done | Peiyou Yao | G4PW-50 | Admin / System Operations | Sprint 3, Sprint 4 | 2 |  | 20/Jun/26 11:51 PM | 24/Jul/26 10:00 AM
G4PW-222 | Implement Location Search and OSM Geocoding Alignment | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 3, Sprint 4 | 2 |  | 20/Jun/26 11:58 PM | 24/Jul/26 9:46 AM
G4PW-226 | Implement Axios/Fetch Token Silent Refresh Interceptors | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 3, Sprint 4 | 3 |  | 22/Jun/26 6:50 PM | 24/Jul/26 9:55 AM
G4PW-230 | Integrate Toggle Heart Icon Mechanics on Web Venue Cards | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 3, Sprint 4 | 2 |  | 22/Jun/26 6:53 PM | 24/Jul/26 9:46 AM
G4PW-234 | Secrets Abstraction, .gitignore Enforcements, and Blueprints | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 3, Sprint 4 | 2 |  | 22/Jun/26 6:58 PM | 25/Jul/26 6:30 PM
G4PW-235 | Test Architecture Isolation & SQLite Pipeline Preservation | Done | Tzu Yu Chang | G4PW-51 | DevOps, Infrastructure & CI/CD | Sprint 3, Sprint 4 | 2 |  | 22/Jun/26 6:59 PM | 30/Jul/26 2:28 PM
G4PW-237 | Calculate Total Items and Update VenueListResponse Schema | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 4 | 2 | 2 | 23/Jun/26 7:23 PM | 07/Jul/26 12:35 PM
G4PW-238 | Implement Numbered Pagination UI for Venue Search | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 4 | 2 |  | 23/Jun/26 7:24 PM | 13/Jul/26 11:59 PM
G4PW-239 | Implement Mobile Pagination Control for Venue Search | Done | Wenfei Song | G4PW-2 | Venue Discovery & Search | Sprint 4 | 2 |  | 23/Jun/26 7:24 PM | 30/Jul/26 2:16 PM
G4PW-243 | Evaluate Area Busyness Model with Error Metrics | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 3, Sprint 4 | 3 |  | 01/Jul/26 12:19 AM | 24/Jul/26 9:55 AM
G4PW-244 | Explore Random Forest Alternative for Busyness Prediction | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 3, Sprint 4 | 3 |  | 01/Jul/26 12:20 AM | 24/Jul/26 9:55 AM
G4PW-255 | Implement backend venue availability endpoint /api/venues/{venue_id}/availability | Done | sunmin.lee | G4PW-4 | Booking & Payments | Sprint 4 | 3 | 3 | 07/Jul/26 1:52 PM | 09/Jul/26 6:57 AM
G4PW-256 | Refactor POST /api/bookings to use authenticated user context instead of client user_id | Done | sunmin.lee | G4PW-4 | Booking & Payments | Sprint 4 | 3 | 3 | 07/Jul/26 1:54 PM | 09/Jul/26 7:46 AM
G4PW-257 | Update web checkout to match final booking API contract | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 4 | 2 |  | 07/Jul/26 2:40 PM | 24/Jul/26 9:46 AM
G4PW-258 | Remove checkout hardcoded fallback booking data | Done | Peiyou Yao | G4PW-4 | Booking & Payments | Sprint 4 | 1 |  | 07/Jul/26 2:40 PM | 24/Jul/26 9:46 AM
G4PW-259 | Integrate mobile checkout with real booking API | Done | Wenfei Song | G4PW-4 | Booking & Payments | Sprint 4 | 4 |  | 07/Jul/26 2:41 PM | 30/Jul/26 2:14 PM
G4PW-260 | Test full booking flow | Done | Tzu Yu Chang | G4PW-4 | Booking & Payments | Sprint 4 | 2 |  | 07/Jul/26 2:42 PM | 25/Jul/26 6:30 PM
G4PW-261 | Validate paginated venue loading and filter persistence | Done | Tzu Yu Chang | G4PW-2 | Venue Discovery & Search | Sprint 4 | 1 |  | 07/Jul/26 3:04 PM | 25/Jul/26 6:30 PM
G4PW-262 | Add backend venue name suggestion endpoint for web search autocomplete | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 4 | 2 | 2 | 07/Jul/26 4:01 PM | 12/Jul/26 11:55 AM
G4PW-263 | Refactor web SearchPage state for separate Map and List venue datasets | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 4 | 3 |  | 07/Jul/26 4:03 PM | 24/Jul/26 9:46 AM
G4PW-264 | Render all landmark-radius venues on Web Map View independent of pagination | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 4 | 3 |  | 07/Jul/26 4:05 PM | 13/Jul/26 11:59 PM
G4PW-265 | Implement web search autocomplete for venues and landmarks | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 4 | 5 |  | 07/Jul/26 4:10 PM | 13/Jul/26 11:59 PM
G4PW-266 | Integrate weighted suitability scoring into backend venue APIs | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 5 | 5 | 07/Jul/26 4:43 PM | 16/Jul/26 9:41 AM
G4PW-267 | Display suitability ranking and recommendation badges on Web Search results | Done | Peiyou Yao | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 5 |  | 07/Jul/26 4:44 PM | 24/Jul/26 9:45 AM
G4PW-268 | Integrate area busyness score into backend venue API response | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 3 | 3 | 07/Jul/26 5:03 PM | 13/Jul/26 5:32 PM
G4PW-269 | Display area busyness score on Web venue cards and map view | Done | Peiyou Yao | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 2 |  | 07/Jul/26 5:04 PM | 24/Jul/26 9:45 AM
G4PW-270 | Validate area busyness score across search and discovery flows | Done | Tzu Yu Chang | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 1 |  | 07/Jul/26 5:05 PM | 25/Jul/26 6:30 PM
G4PW-271 | Integrate Google Gemini API for chatbot backend service | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 3 | 3 | 07/Jul/26 5:09 PM | 12/Jul/26 12:36 PM
G4PW-272 | Convert chatbot venue requests into structured search parameters | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 5 | 5 | 07/Jul/26 5:10 PM | 15/Jul/26 1:47 AM
G4PW-273 | Build web chatbot UI with venue recommendation results | Done | Peiyou Yao | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 5 |  | 07/Jul/26 5:11 PM | 13/Jul/26 11:51 PM
G4PW-274 | Build mobile app chatbot UI with venue recommendation results | Done | Wenfei Song | G4PW-6 | ML Recommendation & AI Features | Sprint 4 | 5 |  | 07/Jul/26 5:25 PM | 24/Jul/26 9:55 AM
G4PW-275 | Add backend API to create user favorite venue | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 4 | 2 | 2 | 07/Jul/26 5:27 PM | 08/Jul/26 4:32 PM
G4PW-276 | Align Missing Venue Fields and API Contract Across All Platforms | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 5 | 3 | 3 | 21/Jul/26 4:19 PM | 22/Jul/26 1:01 PM
G4PW-277 | Complete Search and Availability Filters | Done | sunmin.lee | G4PW-2 | Venue Discovery & Search | Sprint 5 | 2 | 2 | 21/Jul/26 4:49 PM | 22/Jul/26 7:03 PM
G4PW-278 | Integrate Shared Suitability Score into Venue APIs | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 5 | 2 | 2 | 21/Jul/26 4:50 PM | 22/Jul/26 4:55 PM
G4PW-279 | Finalise Shared Suitability Scoring Logic | Done | Adam Treanor | G4PW-6 | ML Recommendation & AI Features | Sprint 5 | 2 |  | 21/Jul/26 5:03 PM | 25/Jul/26 6:29 PM
G4PW-280 | Integrate Existing Busyness Model into Venue APIs | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 5 | 2 | 2 | 21/Jul/26 5:07 PM | 22/Jul/26 1:20 PM
G4PW-281 | Optimize Search Results, List Loading, and Map Marker Density | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 5 | 3 |  | 21/Jul/26 5:08 PM | 24/Jul/26 10:00 AM
G4PW-282 | Upgrade Web Map View to Google Maps | Done | Peiyou Yao | G4PW-2 | Venue Discovery & Search | Sprint 5 | 2 |  | 21/Jul/26 5:10 PM | 25/Jul/26 6:29 PM
G4PW-283 | Remove Mock Venue Images and Redesign Image-Free Layouts | Done | Peiyou Yao | G4PW-3 | Venue Detail | Sprint 5 | 2 |  | 21/Jul/26 5:11 PM | 24/Jul/26 9:45 AM
G4PW-284 | Connect the AI Chatbot to the Venue Database | Done | sunmin.lee | G4PW-6 | ML Recommendation & AI Features | Sprint 5 | 3 | 3 | 21/Jul/26 5:12 PM | 22/Jul/26 5:21 PM
G4PW-285 | Complete Favorites Frontend Integration | Done | Peiyou Yao | G4PW-1 | User Authentication & Account | Sprint 5 | 1 |  | 21/Jul/26 5:13 PM | 25/Jul/26 6:29 PM
G4PW-286 | Connect the Provider Offer Space Form to the Venue API | Done | Peiyou Yao | G4PW-5 | Provider / Venue Management | Sprint 5 | 2 |  | 21/Jul/26 5:16 PM | 24/Jul/26 9:45 AM